## Tham so thuat toan
Tham số thuật toán DLHS
Key | Value
HMS | 60
BW_max | 2
BW_min | 1
PSLSize | 5
numOfSub | 4
R | 100
Max_FEs | 20000

## Thong_Tin_Du_An
ID_KPI_Target | Target A | Target B | Target C
0 | 0 | 0
Start Time | End Time
8/1/2024, 12:00:00 AM | 11/1/2024, 12:00:00 AM

## Ket_qua_phan_bo
Thông tin phân bổ
Task ID (Task Name) | Start Time | End Time | AssigneeId (Assignee Name) | AssetId (Asset Name)
1 (Module 1 - Task 1) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 12 (Emp 12) | [ ]
2 (Module 1 - Task 2) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 2 (Emp 2) | [ ]
3 (Module 1 - Task 3) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 5 (Emp 5) | [ ]
4 (Module 1 - Task 4) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 4 (Emp 4) | [ ]
5 (Module 1 - Task 5) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 1 (Emp 1) | [ ]
6 (Module 1 - Task 6) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 3 (Emp 3) | [ ]
7 (Module 1 - Task 7) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 11 (Emp 11) | [ ]
8 (Module 1 - Task 8) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 9 (Emp 9) | [ ]
9 (Module 1 - Task 9) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 6 (Emp 6) | [ ]
10 (Module 1 - Task 10) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 10 (Emp 10) | [ ]
11 (Module 1 - Task 11) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 7 (Emp 7) | [ ]
12 (Module 1 - Task 12) | 8/1/2024, 12:00:00 AM | 8/7/2024, 8:00:00 PM | 8 (Emp 8) | [ ]
13 (Module 2 - Task 1) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 9 (Emp 9) | [ ]
14 (Module 2 - Task 2) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 1 (Emp 1) | [ ]
15 (Module 2 - Task 3) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 4 (Emp 4) | [ ]
16 (Module 2 - Task 4) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 5 (Emp 5) | [ ]
17 (Module 2 - Task 5) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 11 (Emp 11) | [ ]
18 (Module 2 - Task 6) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 10 (Emp 10) | [ ]
19 (Module 2 - Task 7) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 7 (Emp 7) | [ ]
20 (Module 2 - Task 8) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 2 (Emp 2) | [ ]
21 (Module 2 - Task 9) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 12 (Emp 12) | [ ]
22 (Module 2 - Task 10) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 6 (Emp 6) | [ ]
23 (Module 2 - Task 11) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 3 (Emp 3) | [ ]
24 (Module 2 - Task 12) | 8/7/2024, 8:00:00 PM | 8/26/2024, 10:00:00 AM | 8 (Emp 8) | [ ]
25 (Module 3 - Task 1) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 9 (Emp 9) | [ ]
26 (Module 3 - Task 2) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 2 (Emp 2) | [ ]
27 (Module 3 - Task 3) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 5 (Emp 5) | [ ]
28 (Module 3 - Task 4) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 8 (Emp 8) | [ ]
29 (Module 3 - Task 5) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 10 (Emp 10) | [ ]
30 (Module 3 - Task 6) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 4 (Emp 4) | [ ]
31 (Module 3 - Task 7) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 6 (Emp 6) | [ ]
32 (Module 3 - Task 8) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 1 (Emp 1) | [ ]
33 (Module 3 - Task 9) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 12 (Emp 12) | [ ]
34 (Module 3 - Task 10) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 11 (Emp 11) | [ ]
35 (Module 3 - Task 11) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 7 (Emp 7) | [ ]
36 (Module 3 - Task 12) | 8/26/2024, 10:00:00 AM | 9/10/2024, 10:00:00 AM | 3 (Emp 3) | [ ]
37 (Module 4 - Task 1) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 8 (Emp 8) | [ ]
38 (Module 4 - Task 2) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 5 (Emp 5) | [ ]
39 (Module 4 - Task 3) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 9 (Emp 9) | [ ]
40 (Module 4 - Task 4) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 7 (Emp 7) | [ ]
41 (Module 4 - Task 5) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 10 (Emp 10) | [ ]
42 (Module 4 - Task 6) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 2 (Emp 2) | [ ]
43 (Module 4 - Task 7) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 3 (Emp 3) | [ ]
44 (Module 4 - Task 8) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 6 (Emp 6) | [ ]
45 (Module 4 - Task 9) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 11 (Emp 11) | [ ]
46 (Module 4 - Task 10) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 4 (Emp 4) | [ ]
47 (Module 4 - Task 11) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 1 (Emp 1) | [ ]
48 (Module 4 - Task 12) | 9/10/2024, 10:00:00 AM | 9/21/2024, 10:00:00 AM | 12 (Emp 12) | [ ]
49 (Module 5 - Task 1) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 4 (Emp 4) | [ ]
50 (Module 5 - Task 2) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 8 (Emp 8) | [ ]
51 (Module 5 - Task 3) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 5 (Emp 5) | [ ]
52 (Module 5 - Task 4) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 10 (Emp 10) | [ ]
53 (Module 5 - Task 5) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 2 (Emp 2) | [ ]
54 (Module 5 - Task 6) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 6 (Emp 6) | [ ]
55 (Module 5 - Task 7) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 1 (Emp 1) | [ ]
56 (Module 5 - Task 8) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 11 (Emp 11) | [ ]
57 (Module 5 - Task 9) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 9 (Emp 9) | [ ]
58 (Module 5 - Task 10) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 12 (Emp 12) | [ ]
59 (Module 5 - Task 11) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 7 (Emp 7) | [ ]
60 (Module 5 - Task 12) | 9/21/2024, 10:00:00 AM | 10/7/2024, 6:00:00 AM | 3 (Emp 3) | [ ]
61 (Module 6 - Task 1) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 1 (Emp 1) | [ ]
62 (Module 6 - Task 2) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 5 (Emp 5) | [ ]
63 (Module 6 - Task 3) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 9 (Emp 9) | [ ]
64 (Module 6 - Task 4) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 12 (Emp 12) | [ ]
65 (Module 6 - Task 5) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 11 (Emp 11) | [ ]
66 (Module 6 - Task 6) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 2 (Emp 2) | [ ]
67 (Module 6 - Task 7) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 10 (Emp 10) | [ ]
68 (Module 6 - Task 8) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 7 (Emp 7) | [ ]
69 (Module 6 - Task 9) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 6 (Emp 6) | [ ]
70 (Module 6 - Task 10) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 4 (Emp 4) | [ ]
71 (Module 6 - Task 11) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 8 (Emp 8) | [ ]
72 (Module 6 - Task 12) | 10/7/2024, 6:00:00 AM | 10/11/2024, 10:00:00 AM | 3 (Emp 3) | [ ]
73 (Module 7 - Task 1) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 7 (Emp 7) | [ ]
74 (Module 7 - Task 2) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 4 (Emp 4) | [ ]
75 (Module 7 - Task 3) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 9 (Emp 9) | [ ]
76 (Module 7 - Task 4) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 6 (Emp 6) | [ ]
77 (Module 7 - Task 5) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 11 (Emp 11) | [ ]
78 (Module 7 - Task 6) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 1 (Emp 1) | [ ]
79 (Module 7 - Task 7) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 3 (Emp 3) | [ ]
80 (Module 7 - Task 8) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 5 (Emp 5) | [ ]
81 (Module 7 - Task 9) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 10 (Emp 10) | [ ]
82 (Module 7 - Task 10) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 12 (Emp 12) | [ ]
83 (Module 7 - Task 11) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 8 (Emp 8) | [ ]
84 (Module 7 - Task 12) | 10/11/2024, 10:00:00 AM | 10/16/2024, 2:00:00 PM | 2 (Emp 2) | [ ]
85 (Module 8 - Task 1) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 10 (Emp 10) | [ ]
86 (Module 8 - Task 2) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 5 (Emp 5) | [ ]
87 (Module 8 - Task 3) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 1 (Emp 1) | [ ]
88 (Module 8 - Task 4) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 7 (Emp 7) | [ ]
89 (Module 8 - Task 5) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 6 (Emp 6) | [ ]
90 (Module 8 - Task 6) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 3 (Emp 3) | [ ]
91 (Module 8 - Task 7) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 8 (Emp 8) | [ ]
92 (Module 8 - Task 8) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 4 (Emp 4) | [ ]
93 (Module 8 - Task 9) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 9 (Emp 9) | [ ]
94 (Module 8 - Task 10) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 12 (Emp 12) | [ ]
95 (Module 8 - Task 11) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 2 (Emp 2) | [ ]
96 (Module 8 - Task 12) | 10/16/2024, 2:00:00 PM | 10/20/2024, 8:00:00 AM | 11 (Emp 11) | [ ]
Các kết quả sau khi phân bổ
Target KPI Type A | Result KPI Type A | Target KPI Type B | Result KPI Type B | Target KPI Type C | Result KPI Type C | Start Time | End Time | Total Duration Works | Total Cost | Distance | Performence (s)
0 | 0 | 0 | 0 | 0 | 0 | 8/1/2024, 12:00:00 AM | 10/20/2024, 8:00:00 AM | 80.3333 | 7712 | 0 | 16.3049