## projects
id | key | name | description | start_time | end_time | project_lead
1 | ENTMQMAAS_3xxxx | Module 3-A-MQ Messaging-as-a-Service ( ENTMQMAAS_3xxxx) | Module 3-A-MQ Messaging-as-a-Service (ENTMQMAAS_3xxxx) là một thành phần thuộc nền tảng cung cấp dịch vụ nhắn tin phân tán theo mô hình Messaging-as-a-Service. | 2017-11-14 02:37 | 2020-05-11 04:15 | rgodfrey@redhat.com
2 | ENTMQMAAS_4xxxx | Module 4-A-MQ Messaging-as-a-Service ( ENTMQMAAS_4xxxx) | Module 4-A-MQ Messaging-as-a-Service (ENTMQMAAS_4xxxx) là một thành phần thuộc nền tảng cung cấp dịch vụ nhắn tin phân tán theo mô hình Messaging-as-a-Service. | 2017-11-14 02:37 | 2020-05-11 04:15
3 | ENTMQMAAS_5xxxx | Module 5-A-MQ Messaging-as-a-Service ( ENTMQMAAS_5xxxx) | Module 5-A-MQ Messaging-as-a-Service (ENTMQMAAS_5xxxx) là một thành phần thuộc nền tảng cung cấp dịch vụ nhắn tin phân tán theo mô hình Messaging-as-a-Service. | 2017-11-14 02:37 | 2020-05-11 04:15

## tasks
ID Công việc | ID Project | Mã Công việc | Tên công việc |  | Ước lượng thời gian (ngày) | Yêu cầu năng lực nhân sự | Đảm nhận
Task ID | Project ID | Task Code | Task Name | Lọại cv | Estimate Time | Require Assignee | Assignee
1 | 1 | ENTMQMAAS-318 | Productize ER3 of RHOM | devops | 0.20903 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance:1, system_test: 0] | pkralik
2 | 1 | ENTMQMAAS-334 | [#746] : Add support for checking requests against limits and setting status on address | backend | 41.9646 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
3 | 1 | ENTMQMAAS-335 | [#747] : Add support for colocated topics | backend | 30.0153 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
4 | 1 | ENTMQMAAS-337 | [#749] : Use statefulsets for brokers | backend | 8.9646 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
5 | 1 | ENTMQMAAS-332 | [#744] : Implement Plan resource limits for address space | backend | 14.1292 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
6 | 1 | ENTMQMAAS-336 | [#748] : Persist decision about where queues/topics are placed | backend | 41.966 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
7 | 1 | ENTMQMAAS-333 | [#745] : Implement Plan resource requests for addresses | backend | 14.1299 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
8 | 1 | ENTMQMAAS-340 | [#752] : Need to be able to configure address-controller to use wildcard cert for route certs | security&maintenance | 42.0632 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
9 | 1 | ENTMQMAAS-355 | [#767] : Disable durable subs (configurable upstream?) | backend | 56.0278 | [ year_of_exp: 5, backend: 1, bugfixing&debugging: 2, devops: 0, docs: 0, security&maintenance: 1, system_test: 0] | gordonsim
10 | 1 | ENTMQMAAS-349 | [#761] : Console to support status for addresses | backend | 31.2792 | [ year_of_exp: 5, backend: 1, bugfixing&debugging: 2, devops: 0, docs: 0, security&maintenance: 1, system_test: 0] | gordonsim
11 | 1 | ENTMQMAAS-339 | [#751] : Use valid wildcart cert | security&maintenance | 64.8896 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 0] | rgodfrey@redhat.com
12 | 1 | ENTMQMAAS-350 | [#762] : How to match plans offered to plans specified (e.g. have console offer plans based on the presence of configmaps in its namespace or variations of that) | backend | 30.1014 | [ year_of_exp: 5, backend: 1, bugfixing&debugging: 2, devops: 0, docs: 0, security&maintenance: 1, system_test: 0] | gordonsim
13 | 1 | ENTMQMAAS-343 | [#755] : Productize: router, queue-scheduler, standard-controller, alter keycloak to be init-container image | devops | 42.1576 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 0] | rgodfrey@redhat.com
14 | 1 | ENTMQMAAS-356 | [#768] : Disable MQTT (configurable upstream?) | backend | 36.1604 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
15 | 1 | ENTMQMAAS-341 | [#753] : Tie user identity creating address spaces and addresses to billing (i.e. reliable record of addresses spaces used against some identity for the customer) | backend | 42.1583 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 0] | rgodfrey@redhat.com
16 | 1 | ENTMQMAAS-345 | [#757] : Oauth for console | security&maintenance | 70.8917 | [ year_of_exp: 5, backend: 1, bugfixing&debugging: 2, devops: 0, docs: 0, security&maintenance: 1, system_test: 0] | gordonsim
17 | 1 | ENTMQMAAS-346 | [#758] : Keycloak plugin OAUTH2 support | security&maintenance | 63.134 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 0] | rgodfrey@redhat.com
18 | 1 | ENTMQMAAS-357 | Polarion reporting of enmasse test cases | docs | 14.0243 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
19 | 1 | ENTMQMAAS-361 | [#773] : Tests for authentication WebConsole | system test | 16.0146 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
20 | 1 | ENTMQMAAS-362 | [#774] : Tests for authorization in WebConsole | system test | 13.9028 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
21 | 1 | ENTMQMAAS-358 | [#770] : Define tests for limitation of address-spaces (by credits) | system test | 30.0743 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
22 | 1 | ENTMQMAAS-360 | [#772] : WebConsole Tests for addresses status | system test | 34.9674 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
23 | 1 | ENTMQMAAS-364 | [#776] : Recheck and enable system tests for standard address space | system test | 15.9049 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
24 | 1 | ENTMQMAAS-363 | [#775] : Tests for clients authorization | system test | 13.9021 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
25 | 1 | ENTMQMAAS-365 | [#777] : Rewrite Jenkinsfile-long to declarative pipeline syntax | devops | 29.891 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
26 | 1 | ENTMQMAAS-367 | Setup Jenkins job with productized images | devops | 58.9056 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
27 | 1 | ENTMQMAAS-374 | [#843] : improve test framework regarding to definition of dynamically created plans | system test | 15.9201 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
28 | 1 | ENTMQMAAS-375 | [#844] : system-tests: create documentation in HACKING doc how to execute webconsole tests | docs | 6.7986 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
29 | 1 | ENTMQMAAS-382 | Investigate options for enforcing backlog limits on broker/router | backend | 30.8493 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
30 | 1 | ENTMQMAAS-383 | [#811] : Brokered: cannot create topic: user null does not have permissions to 'send'... | security&maintenance | 2.9604 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 0] | rgodfrey@redhat.com
31 | 1 | ENTMQMAAS-384 | [#877] : Make ansible deployment for install dependencies for running systemtests | devops | 7.9167 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
32 | 1 | ENTMQMAAS-385 | [#894] : Console does not sanitize address config names | bugfixing&debugging | 7.0424 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
33 | 1 | ENTMQMAAS-386 | [#910] : address-controller can't replace addresses created via console | bugfixing&debugging | 5.809 | [ year_of_exp: 5, backend: 3, bugfixing&debugging:2, devops: 2, docs: 0, security&maintenance: 2, system_test: 0] | lulf@redhat.com
34 | 1 | ENTMQMAAS-387 | [#918] : system-tests: new scale test: testScaleRouterAutomatically | system test | 26.15 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
35 | 1 | ENTMQMAAS-388 | [#919] : system-tests: new scale test: testPodsLimitation | system test | 14.8778 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
36 | 1 | ENTMQMAAS-389 | [#920] : system-tests: new scale test: testCreditLimitation | system test | 11.8792 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
37 | 1 | ENTMQMAAS-390 | [#921] : system-tests: new Plan test: testPlansAvailableViaConsole | system test | 11.7792 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
38 | 1 | ENTMQMAAS-391 | [#936] : system-tests: create new test for thorough testing of REST API for address/address-space | system test | 14.0639 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
39 | 1 | ENTMQMAAS-393 | [#991] : system-tests: new scale test: testCreditLimitation ({sharded,pooled}{queues,topics}) | system test | 2.2035 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
40 | 1 | ENTMQMAAS-395 | [#996] : system-tests: look at longtime running tests and fix them | system test | 2.9813 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
41 | 1 | ENTMQMAAS-396 | [#907] : system-tests: add parametr for disable 'tear down' methods in systemtests | system test | 16.959 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
42 | 1 | ENTMQMAAS-397 | [#997] : system-tests: rewrite to junit5 2. step (reduce inheritance of TestBases) | system test | 42.9813 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
43 | 1 | ENTMQMAAS-398 | System-tests: periodical maintenance of systemtests and CI | devops | 24.1701 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
44 | 1 | ENTMQMAAS-399 | [#998] : system-tests: review list of February disabled tests | system test | 3.0319 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
45 | 1 | ENTMQMAAS-306 | Unable test io.enmasse.systemtest.brokered.clients.rhea.MsgPatternsTest.testMessageSelectorTopic | bugfixing&debugging | 0.74931 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
46 | 1 | ENTMQMAAS-305 | [#526] : System-tests: November list of disabled tests | system test | 16.891 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
47 | 1 | ENTMQMAAS-303 | [#523] : SystemTests: brokered/standard: new test for keycloak persistent storage | system test | 50.7875 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 0, devops: 0, docs: 0, security&maintenance: 0, system_test: 1] | tkratky_jira
48 | 1 | ENTMQMAAS-307 | [#539] : System-tests: createtestAuthSendReceiveLong | system test | 12.7687 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
49 | 1 | ENTMQMAAS-304 | [#524] : System-tests: longtime: create new test for user authentication before/after restarting keycloak | system test | 14.7639 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com
50 | 1 | ENTMQMAAS-301 | [#516] : System-tests: create testCreateDeleteAddressesViaAgentLong | system test | 90.9826 | [ year_of_exp: 5, backend: 0, bugfixing&debugging: 1, devops: 2, docs: 1, security&maintenance: 0, system_test: 4] | dkornel@redhat.com